## Start here
Strategy implementation plan
A template for turning a chosen strategy into work, with the reasons for the strategy kept beside the tasks.
1. Fill in the Strategy sheet first. The plan only makes sense next to the reasons the strategy was chosen.
2. List the initiatives: the larger pieces of work, each with an owner, a target date, a sub-goal and a measure.
3. Break each initiative into plans and tactics, ranked so the team knows what comes first.
4. Go back to the Strategy sheet when one of its review triggers fires.
The grey text is a worked example for Larkhill Roasters, a fictional coffee roaster. Write your answers beside it on the Strategy sheet, then write over the example rows on the other two.
The guide that goes with this template: https://wayframer.com/learn/strategy-implementation-plan
In Wayframer the same plan builds as you work out the strategy, and travels into the Implementation Pack: https://wayframer.com

## Strategy
Part | Your answer | What goes here | Example: Larkhill Roasters
Endeavor |  | The goal this plan serves, in one line. | Double Larkhill Roasters in three years.
Aspiration |  | Where you mean to be, stated so you would know when you got there. | Double revenue in three years while protecting the quality and identity that make us good.
Diagnosis |  | The main thing in the way: the bottleneck the strategy has to get past. | Working capital. Customers pay at sixty days and suppliers want payment at thirty, so we cannot fund the green coffee that rising demand needs.
Strategy chosen |  | The alternative left standing. | Scale wholesale to independent cafés and restaurants.
Why it was chosen |  | The fitness criteria it met. | Inbound demand and spare roasting capacity, with no fit-outs to fund.
Ruled out, and why |  | The alternatives that could not fit, each with its reason. | More cafés in the South West: fit-outs need funding we cannot raise. A coffee subscription: small volumes leave most of the spare capacity idle.
What it rules out |  | What the choice means you will stop doing, or will not start. | No new cafés of our own in this period.
Review triggers |  | The conditions that would send you back to the choice. | Fewer than two thirds of trial accounts reorder within a month. Green coffee costs rise faster than we can pass them on.
Owner |  | Who owns the strategy. | The founder.
Next review |  | When the team will next check the choice against what has happened. | The end of each quarter.

## Initiatives
Initiative | Owner | Target date | Sub-goal | Measure | How it serves the strategy | Status
Open three new wholesale accounts a month | Sales lead | 30 June | Twelve new accounts by the end of June | New accounts opened each month | Turns inbound demand into regular orders. | Under way
Fund green coffee for wholesale | Finance lead | 31 March | Thirty-day terms agreed with every new café account | Days between paying for green coffee and being paid for it | Gets past the working capital bottleneck. | Not started

## Plans and tactics
Rank | Plan or tactic | Initiative it serves | Owner | Due | Done
1 | Call every café that enquired about wholesale in the last six months | Open three new wholesale accounts a month | Sales lead | Week 2 | No
2 | Offer new cafés a two-week trial supply | Open three new wholesale accounts a month | Sales lead | Week 4 | No
3 | Ask the green coffee supplier for sixty-day terms | Fund green coffee for wholesale | Finance lead | Week 3 | No